## Completion Status
FS Sign Off Scope PVI | Type | BISP Status | Remarks
Dashboard | Initial Requirement | Partially Done | Dashboard is designed based on the KPI that are discovered during the development, but there is a need to coordinate the KPI's from user wing.
Filter Management
Geolocation | Initial Requirement | Done | Geolocation filter is defined to filter dataset on the basis of Province, District and Tehsils.
Eligible/ Active Beneficiary | Initial Requirement | Done | Beneficiary Eligibility Criteria based on Account activation date and beneficiary status
Filter Reports | Change Request | Done | Pre Payment Reports based on each filter
Payment Generation (UCT)
Payment Configuration | Initial Requirement | Done | Payment Configuration includes Fiscal Year Mapping, Number of moths, Payment Amount and Cut off date
Applying Filter on Payment | Initial Requirement | Done | Applying defined filters on payment instance
Payment Summaries Generation | Change Request | Done | Summaries are generated for each payment that includes Province Base Summary, Cluster Base Summary, Reason Base Summary and Bank/Payment Agency Base Summary
Payment Dashboard | Initial Requirement | Done | Dashboard is designed for each payment to review the details of each payment
Payment Verification
MIS payment Summaries Mapping | Change Request | Done | Extracting MIS Payment data and mapping of summaries attribute in PVI
Validating PVI payment with MIS payment | Initial Requirement | Done | Comparison of MIS & PVI generated payments and displaying the results
Identification of discrepant records | Initial Requirement | Done | Identification of discrepant beneficiaries in MIS and PVI pyments
Program Trench Management
Fiscal Year and Amount Configuration | Change Request | Done | Fiscal Year definition and amount for each time period is defined
Reason Management
Beneficary Reason & Status Management | Initial Requirement | Done | Displaying the existing benficiary reason and respective dataset reports
Payment Log/ History
Payment Detail | Initial Requirement | Pending | Need MIS Wing review to identify the type of transaction on which the log/ history is required.
Arrear Management | Change Request | Pending | MIS Wing is working and cordinating with stakeholders, on definig a process to generate and manage these payments
Special Payment
Retrospective Payment

## Sheet1
Developed Features | Verification from Customer | Pending Knowledge | TOR Objectives | Out of Scope
Dashboard | Verified | Payment Log/ History | Ensure accouracy of amount & data for UCT, CCT, Arrear & Special tranch | Reason Management
Filter Management |  | Payment Detail | Cross Verification with MIS Payment | Reason Filter
GeoLocation Filter | Verified | Payment Features | Payment Verification by Province, District, Mode & Arears | Fiscal Year and Amount Configuration
Beneficiary Status Filter | Verified | Arrear Management | Current Tranche comparison with last tranche | Arrear Management
Reason Management Status | Verified | Special Payment | Multi user | Special Payment
Filter Reports | Verified | Retrospective Payment | Drilldown Analysis | Retrospective Payment
Payment Generation
Payment Configuration | Verified
Applying Filter on Payment | Verified
Payment Summaries Generation | Verified
Payment Dashboard | Verified
Payment Verification
MIS payment Summaries Mapping | Verified
Validating PVI payment with MIS payment | Verified
Identification of discrepant records | QA Review Pending
Program Trench Management
Fiscal Year and Amount Configuration | QA Review Pending
Reason Management
Beneficary Reason & Status Management | QA Review Pending
Assessment of Payment Generation By MIS
Design & Development of PVI
Installing & Training of Application
Deliverables
Technical Specification
Preliminary Report
Technical Design Document
Application Installation
User Manual